## Development Plan
Phase | Step | Component / Project | Task | Duration | Status
Phase 1 | Step 1 | Repository & Solution Setup | Setup solution structure, shared libraries, environment config | 0.5 Day | Pending
Phase 1 | Step 2 | Shared Platform Libraries | Create DTOs, contracts, enums, domain entities | 0.5 Day | Pending
Phase 1 | Step 3 | Database Setup | Configure SQL DB, EF Core, migrations, repositories | 0.5 Day | Pending
Phase 2 | Step 4 | Device Simulator | Implement telemetry, heartbeat, smoke/heat event simulation | 0.5 Day | Pending
Phase 2 | Step 5 | Gateway API | Device ingestion, validation, authentication, normalization | 0.5 Day | Pending
Phase 2 | Step 6 | Listener | Consume payloads, enrich events, publish to EventBus | 0.5 Day | Pending
Phase 2 | Step 7 | EventBus Integration | Kafka / Azure Service Bus setup and topic creation | 0.5 Day | Pending
Phase 3 | Step 8 | Workflow Orchestrator | Runtime routing and workflow sequencing | 0.5 Day | Pending
Phase 3 | Step 9 | Processor Runtime | Rule evaluation, correlation logic, alarm generation | 1 Day | Pending
Phase 3 | Step 10 | Cache Layer | Runtime cache and recent event tracking | 0.5 Day | Pending
Phase 4 | Step 11 | Action Dispatcher | Alarm handler, incident handler, SignalR broadcast handler | 0.5 Day | Pending
Phase 4 | Step 12 | Persistence Flow | Persist events, alarms, incidents, history | 0.5 Day | Pending
Phase 5 | Step 13 | API Layer | Dashboard APIs, SignalR hubs, incident APIs | 0.5 Day | Pending
Phase 5 | Step 14 | SignalR Integration | Real-time event broadcasting and monitoring | 0.5 Day | Pending
Phase 5 | Step 15 | Dashboard UI | Dashboard, alerts, monitoring, incident history | 1 Day | Pending
Final | Testing & Demo | End-to-End Runtime Flow | Demo scenarios, bug fixes, final polishing | 1 Day | Pending

## Runtime Flow
Sequence | Component | Status
1 | Device Simulator
2 | Gateway API
3 | Listener
4 | Kafka / EventBus
5 | Workflow Orchestrator
6 | Processor Runtime
7 | Action Dispatcher
8 | SignalR / API
9 | Web Dashboard

## 1 Week Plan
Day | Focus Area | Status
Day 1 | Repository Setup + Shared Libraries + Database
Day 2 | Device Simulator + Gateway API
Day 3 | Listener + Kafka/EventBus
Day 4 | Workflow Orchestrator + Runtime Processor
Day 5 | Action Dispatcher + Persistence
Day 6 | API Layer + SignalR + Dashboard UI
Day 7 | Testing + Demo Flow + Final Polish